## Project Plan
R2R - Draft Version
Sl No | module/Task | Owner | Status | Estimated No of Working Days | Estimated Start Date | Estimated End Date | Comments | Dependencies/ Comments
1 | Solution Design | Prabhakar/ Prakash | In - Progress
1.1 | High level Solution Design |  | Completed |  |  |  | Detailed plan to keep evolving over the tenure of project
1.2 | Detailed view of Solution Design |  | In - Progress
2 | UI Design | Shameem | Yet to Start |  | 2017-09-18 | 2017-09-30
2.1 | Windows based UI ( Using Telerik components / Framework for Desktop UI )
2.2 | Project -Screen
2.3 | Project - Configuration scren
2.4
2.5
3 | Frequentyl Used Modules collction - Chennai Team | Shameem | Completed
3.1
3.2
3.3
3.4
4 | Frequentyl Used Modules collction - Bangalore Team | Rasool | Completed
4.1
4.2
4.3
4.4
5 | Priororization of mdules to be included | Rasool, Shameem, Prakash, Prabhakar | Completed
5.1
5.2
5.3
6 | Working on Class File Generation | Rasool | Yet to Start |  | 2017-09-20 | 2017-10-10
6.1 | WEB Crawling-Login | Anil | [5 empty] | Continous activity. Spread across the tenure of the project
6.2 | GMB-GMB | Magesh
6.4 | -Web Service Connectivity | Mahalakshmi |  |  |  |  | Example OIS ( send a Request and get a Response), Provide a URL, Parameters, Credentials and get the response.
6.5 | WEB Crawling-3W - Specific | Delia
6.6 | DB-DB Connect - SQL Server | Krishna
6.7 | DB-DB Connect - Excel | Krishna
| Document-Parse PDF ( Priority low and may slip to next sprint) | Prabhakar / Naveen |  |  |  |  | Parsr PDF -- Using Nuance, reading PDF and image both 1. Converting image PDF to HTML
| Code Review | Rasool /Prabhakar/Shameem/ Krishna |  |  | 2017-10-01 | 2017-10-10 | come up with general consences based on any standards. Ex : Camle hump otation Etc.
| SAP connect | Naveen
7 | Working on Solution file Generation and Adding References runtime | Shameem | Yet to Start |  | 2017-09-20 | 2017-09-25
7.1
7.2
7.3
8 | Integration of activity 6 and 7 | Rasool /Shameem |  |  | 2017-10-08 | 2017-10-12
8.1
8.2
8.3
9 | Prototype with Simple Modules | Rasool /Shameem |  |  | 2017-10-13 | 2017-10-15
9.1
9.2
9.3
10 | Extending the functionalities beyond Prototype | Rasool /Shameem |  |  | … | …
10.1
10.2
10.3

## Modules-Functions
Category | Priority | Items | Possible Input Variables | Possible Output |  | Description
WEB Crawling | 1 | Login | URL, Browser, User Name, Password,…
GMB | 2 | GMB | Exchange Server, .. , … ,
Document | 3 | Parse PDF | PDf Document | HTML, Json, Array
| 4 | Web Service Connectivity | Service/Method…
WEB Crawling | 5 | 3W - Specific |  |  | Delia and Hemanth
DB | 6 | DB Connect - SQL Server | Server, User, Password,
DB | 7 | DB Connect - Excel | Server, User, Password,
DB | 8 | GetDetailsFromDB | connection, Table, Fields,
DB | 9 | UpdateToDB | connection, Table, Fields,
WEB Crawling | 10 | Web Crawling - Generic
SAP | XXX | Read From SAP Table/Grid | SAP Window…
SAP | XXXX | SAP Connect
| WEB Crawling | 1 | Login | WEB Crawling-Login
| GMB | 2 | GMB | GMB-GMB
| Document | 3 | Parse PDF | Document-Parse PDF
|  | 4 | Web Service Connectivity | -Web Service Connectivity
| WEB Crawling | 5 | 3W - Specific | WEB Crawling-3W - Specific
| DB | 6 | DB Connect - SQL Server | DB-DB Connect - SQL Server
| DB | 7 | DB Connect - Excel | DB-DB Connect - Excel

## Resource Plan
R2R - Draft
| UI Developer | Module Developers | Integrators